## Risk Tracking Template
Risk Register
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Developer unavailable near sprint deadlines | Critical feature delays | Use JIRA to reassign tasks and ProjectLibre to shift timelines | High | Salma | Make sure the task is redistributed equally
2 | VSCode Github extension conflicts on different setups | Delays in coding due to inconsistent environments | Standardize extensions and share workspace settings | High | Marina | Add a setup guide in repo
3 | Missed task updates on JIRA | Confusion about progress and responsibilities | Weekly check-ins; enable JIRA email alerts | Medium | Salma | Use dashboards for visual clarity
4 | Merge conflicts during collaboration | Code breaks or lost functionality | Use Git branches carefully and pull before push | Medium | Mariam | Do weekly code reviews
5 | Bugs found late in testing | Delayed delivery, need for rework | perform manual testing at end of every sprint | Medium | Mariam | Create test checklist in shared doc
6 | ProjectLibre file corruption | Loss of project timeline and dependencies | Regularly back up the file on shared drive | Medium | Mariam | Keep two offline backups
7 | Internet issues during submission or presentations | Delay in delivery or miscommunication | Prepare offline backup files and slides | Low | Marina | Keep a local PDF and offline demo
8 | Overworking or burnout near deadline | Decrease in quality, missed key issues | Set realistic sprint goals and hold team check-ins | Mediun | Salma | Use weekly retrospectives
9 | Inconsistent naming conventions in code | Confusion and increased bugs during integration | Agree on naming conventions and folder structure early | Medium | Mariam | Add code style rules to repo README
10 | Last-minute GitHub issue push failure | Incomplete or failed submission | Ensure final commit is pushed 6 hours before deadline | High | Salma | Assign one person for final push
11 | Misunderstood task requirements from instructor | Building incorrect features or missing expectations | Clarify all tasks during weekly check-ins or via email | Medium | Marina | Keep a shared requirements doc
12 | No clear division of roles | Overlapping work or tasks being left undone | Assign roles in JIRA and confirm in kickoff meeting | High | Marina | Revisit roles during retrospectives
13 | Design inconsistencies across pages | Visual confusion for users | Create a shared design system or component library | Low | Salma | Use consistent button colors and fonts
14 | Missed internal deadlines before final milestone | Rushed implementation, poor code quality | Break down tasks into weekly subtasks with buffers | High | Mariam | Track burndown in JIRA
15 | Incomplete documentation of features or instructions | Confusion during evaluation or future handover | Allocate time for writing user and developer documentation | Medium | Salma | Use README + screenshots + code comments
16 | Sudden team member withdrawal | Task delays and increased pressure on remaining members | Cross-train members and document all work clearly | High | Marina | maintain updated tasks documentation for quick handover
17 | Environment differences between dev and deployment systems | Unexpected bugs during deployment | Set up a staging environment that mirrors production | Medium | Marina | Test deployment regularly before final release
18 | Lack of stakeholder feedback during development | Misaligned product with user needs | Schedule regular demos and feedback sessions with stakeholders | Medium | Marina | Use forms/surveys to gather structured feedback
19 | Incomplete testing coverage | Undetected bugs and reliability issues | Create and maintain test cases for all features, use test coverage tools | High | Marina | Include test metrics in sprint review