## Quality Control Template
Quality Control
Issue | Description | Imperfections | Identified By | To Be Fixed By | Priority | Status | Date Opened | Date Closed | Notes
Authentication | Login fails on incorrect password or doesn't show error | 6 | Mariam | Salma | Critical | Open | 2025-05-10
Pet Image Upload | Image uploader crashes on certain image types | 4 | Salma | Mariam | High | Closed | 2025-05-08 | 2025-05-10
Chat Component | Chat box scroll breaks after 10+ messages | 5 | Marina | Mariam | Medium | Open | 2025-05-09
Adoption Request Form | Submitting form sometimes causes silent failure | 3 | Salma | Mariam | Medium | Open | 2025-05-10
Dashboard Nav | Back button sometimes redirects to wrong section | 2 | Mariam | Marina | Low | closed | 2025-05-07 | 2025-05-08
User Profile Edit | Edited details sometimes not saved after refresh | 4 | Salma | Marina | High | Closed | 2025-05-11 | 2025-05-13
Shelter Search | Shelter search returns incorrect results for keywords | 4 | Salma | Mariam | Medium | Open
Responivenes on Small Screens | Elements in inbox and chat misaligned on small screens | 7 | Mariam | Salma | High | Open | 2025-05-13
Button Feedback | Adoption button gives no visual confirmation after being clicked | 1 | Mariam | Salma | Low | Open | 2025-05-13